## Sprint 1
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
Weekly meeting discussion | Discussion | 2024-03-12 | EVERYONE | DONE | 2024-03-12 | Meeting from 8:30pm - 10:00pm, project was split into separate parts and user stories were drafted based on these parts.
Weekly meeting discussion | Discussion | 2024-03-20 | EVERYONE | DONE | 2024-03-20 | Meeting from 8:30pm - 10:00pm; members came together to work on the domain model, which is to be checked during the next class.
Ad-hoc in-person meeting |  | 2024-03-25 | EVERYONE | DONE | 2024-03-25 | Meeting from 4:00 - 6:00pm; members discussed the initial basic UI design
Weekly meeting discussion | Discussion | 2024-03-26 | EVERYONE | DONE | 2024-03-26 | Meeting from 5:30 - 7:45pm; Finalising all Sprint 1 deliverables, and preparing for submission.
Task 1: Team Information |  | 2024-03-12 | EVERYONE | DONE | 2024-03-25
Task 2: User Stories |  | 2024-03-12 | EVERYONE | DONE | 2024-03-26
Task 3: Domain Model |  | 2024-03-20 | EVERYONE | DONE | 2024-03-26
Task 4: Basic UI Design |  | 2024-03-25 | EVERYONE | DONE | 2024-03-26
Final Submission |  | 2024-03-27 | EVERYONE | DONE | 2024-03-27 | Submitted to Moodle and pushed to GIT after the agreement from all members.

## Sprint 3
Task/Contribution(~30 words) | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
Read through and discuss the Sprint 3 brief | 2024-04-30 | EVERYONE | DONE | 2024-04-30 | The team meeting took place from 6:00pm - 7:00pm. We created a checklist of all the tasks to do and the relative order we plan on completing them in. We also discussed and clarified questions about the brief.
Delegate work for each member and create report | 2024-05-01 | EVERYONE | DONE | 2024-05-01 | The team meeting took place from 7:30pm - 8:30pm. We created the report based on the templates used in Sprint 1 and 2. We created a sublist under out task checklist, which we filled with each team members delegated tasks.
Discord call demonstrating and reviewing the prototypes | 2024-05-03 | EVERYONE | DONE | 2024-05-03 | The team meeting took place from 6:00pm - 8:15pm. Each member shared they're screen to run the prototype whilst the others reviewed the code.
Finalised prototype reviews and chose base prototyope | 2024-05-04 | EVERYONE | DONE | 2024-05-04 | The team meeting took place from 7:00pm - 9:30pm. We discussed the advantages and disadvantages of each prototype and each team member created a list of preferences. The final decision was made and the code was merged into the main branch.
Weekly meeting discussion | 2024-05-06 | EVERYONE | DONE | 2024-05-07 | During this week's workshop, we clarified some questions regarding CRC cards with a teaching assistant. After the workshop, we briefly met to discuss the completion deadline for the UML class diargram and CRC cards. The progress seems to be on track.
Reviewed UML class diagram and CRC cards | 2024-05-09 | EVERYONE | DONE | 2024-05-09 | The team meeting took place from 5:00pm - 6:00pm. We reviewed the UML class diagram and discussed possible modifications or extensions that need to be made to include the full functionality of the game. The CRC cards are finalised for the existing classes.
Weekly meeting discussion | 2024-05-14 | EVERYONE | DONE | 2024-05-14 | The team meeting took place from 5:30pm - 6:30pm We followed up with each member regarding their delegated tasks. The progress seems to be on track.
Prototype team check in | 2024-05-15 | EVERYONE | DONE | 2024-05-15 | The team meeting took place from 8:00pm - 8:45pm. The software prototype has a couple of issues, but most features have been implemented. It may also require some abstraction for clarity. The progress seems to be on track.
Prototype team check in | 2024-05-16 | EVERYONE | DONE | 2024-05-16 | The team meeting took place from 6:00pm - 8:00pm. We finalised the software prototype and performed thorough testing. Internal documentation was added and the video demonstration was planned.
Reviewed UML class diagram and CRC cards | 2024-05-18 | EVERYONE | DONE | 2024-05-18 | The team meeting took place from 8:00pm - 9:30pm. The class diagrams were edited to reflect the changes and the final CRC cards were filled in. The progress seems to be on track.
Record video on Zoom | 2024-05-19 | EVERYONE | DONE | 2024-05-19 | The team meeting took place from 5:00pm - 6:00pm. We setup the prototype and recorded the demonstration.
Final submission meeting | 2024-05-20 | EVERYONE | DONE | 2024-05-20 | The team meeting took place from 8:00pm - 10:00pm. The materials were collated and the final video was remade due to issues with clarity.

## Sprint 4
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes

## Options
Name | Status | Task types
BRANDON LUU | DONE
JEREMY OCKERBY | IN-PROGRESS
RAYMOND LI | INCOMPLETE
MAX ZHUANG | TODO
EVERYONE